# Initial Project Plan

## FYP-T2B (Agile / Iterative Model)

# 1. Project Overview

| Field | Details |
| --- | --- |
| Project Title | A Hybrid Intelligent System for Patient Query Handling and Appointment Management with Guided Patient-to-Department Routing, Urgency-Based Escalation, and Structured Human Handoff Support |
| Group ID | FYP-2026-G2 |
| Student Name(s) | Ibtisam Saleem (SU/BSCS/201/2023), Faryal Israr (SU/BSCS/202/2023) |
| Supervisor | Ma’am Madiha Zaidi |
| Academic Year | 2026 |
| Project Duration | FYP-I to FYP-II |
| Development Model | Agile / Iterative |
| GitHub Repository Link | https://github.com/ibtisamkhan369-ik/FYP-2026-G2-HybridIntelligentSystemforPatientQueryHandlingAndAppointmentManagement |
| Version | 1.0 |
| Date | 11 June 2026 |

# 2. Product Vision

This project aims to develop a hybrid intelligent healthcare support system for hospitals and clinics so that patients can efficiently obtain information, receive guided department recommendations, book appointments, and communicate with healthcare staff through a structured and user-friendly platform.

The system combines chatbot-based patient interaction, appointment management, urgency-aware escalation, and structured human handoff support to improve patient experience while reducing administrative workload.

# 3. Project Objectives

- To develop a web-based patient query handling and appointment management system.

- To implement guided patient-to-department routing using rule-based intent classification.

- To provide appointment scheduling and management through a simulated hospital database.

- To implement urgency-aware escalation for critical patient queries.

- To generate structured human handoff summaries for escalated cases.

- To validate the proposed solution through testing, evaluation, and documented evidence.

# 4. Scope Reference

## In Scope

| S. No. | In-Scope Item |
| --- | --- |
| 1 | Chatbot-based patient interaction |
| 2 | Guided patient-to-department routing |
| 3 | Appointment booking and management |
| 4 | Urgency-aware escalation |
| 5 | Human handoff summary generation |
| 6 | Staff/Admin dashboard |
| 7 | Voice interaction (Speech-to-Text and Text-to-Speech) |
| 8 | Interaction logging and monitoring |
| 9 | Optional WhatsApp integration |
| 10 | Simulated hospital database |

### Out of Scope

| S. No. | Out-of-Scope Item |
| --- | --- |
| 1 | Emergency medical diagnosis |
| 2 | Direct integration with real hospital databases |
| 3 | Billing and payment processing |
| 4 | Electronic Medical Records (EMR) integration |
| 5 | Full telecom/call center infrastructure |
| 6 | Production-scale deployment |
| 7 | AI-generated medical advice |
| 8 | Dedicated mobile application |

# 5. Development Model and Justification

| Item | Details |
| --- | --- |
| Selected SDLC Model | Agile / Iterative |
| Reason for Selection | Requirements, workflows, routing rules, escalation handling, and user interfaces may evolve after supervisor feedback, prototype reviews, and testing activities. Agile development allows incremental improvement and continuous refinement. |
| Sprint / Iteration Duration | Approximately 2–4 weeks, aligned with academic checkpoints. |
| How progress will be monitored | Supervisor meetings, GitHub commits, sprint reviews, checkpoint evaluations, documentation reviews, and prototype demonstrations. |
| How changes will be controlled | Proposed changes will be reviewed with the supervisor and documented through updated requirements, design artifacts, and repository records. |

# 6. Team Structure and Module Ownership

| Student Name | Assigned Role | Primary Responsibilities | Expected Deliverables |
| --- | --- | --- | --- |
| Ibtisam Saleem | Backend & Database Lead | Backend development, database design, appointment logic, intent processing, escalation workflow, API development | Database schema, backend modules, API implementation, integration evidence |
| Faryal Israr | Frontend & Testing Lead | UI/UX design, frontend development, dashboards, testing, documentation support | User interfaces, dashboards, test cases, testing evidence |
| Both Members | Documentation & Integration | SRS, architecture, project planning, integration, final report, presentation preparation | Project documents, integrated prototype, final deliverables |

# 7. Product Backlog

| Backlog ID | User Story / Feature | Priority | Owner | Planned Sprint |
| --- | --- | --- | --- | --- |
| PB-1 | Patient Registration and Login | Must | Ibtisam | Sprint 3 |
| PB-2 | Chatbot Query Processing | Must | Ibtisam | Sprint 3 |
| PB-3 | Guided Department Routing | Must | Ibtisam | Sprint 3 |
| PB-4 | Appointment Booking and Scheduling | Must | Ibtisam | Sprint 3 |
| PB-5 | Reception Staff Dashboard | Must | Faryal | Sprint 3 |
| PB-6 | Department Staff Escalation Management | Must | Faryal | Sprint 3 |
| PB-7 | Urgency Classification and Escalation | Must | Ibtisam | Sprint 3 |
| PB-8 | Human Handoff Summary Generation | Must | Ibtisam | Sprint 3 |
| PB-9 | Voice Interaction Features | Should | Both | Sprint 4 |
| PB-10 | WhatsApp Integration Layer | Could | Both | Sprint 4 |
| PB-11 | Activity Logging and Monitoring | Must | Both | Sprint 4 |
| PB-12 | Final Testing and Validation | Must | Both | Sprint 4 |

# 8. Sprint / Iteration-wise Project Plan

| Sprint / Iteration | Goals | Main Activities | Expected Deliverables | Responsible Student(s) | Tentative Timeline |
| --- | --- | --- | --- | --- | --- |
| Prototype Sprint | Validate project feasibility and requirements | Topic approval, proposal preparation, scope definition, initial planning | Topic Approval Form, Proposal Defence Presentation | Both | FYP-I Weeks 1–7 |
| Sprint 1 – Requirements & Architecture | Establish requirements and technical direction | SRS preparation, literature analysis, architecture design, risk analysis, project planning | SRS, Existing Solutions Analysis, Architecture & Risk Analysis, Project Plan | Both | FYP-I Weeks 8–13 |
| Sprint 2 – Design & MVP | Prepare detailed design and prototype | ERD, database schema, UML diagrams, UI planning, prototype development | Software Design Document, ERD, UML Models, Prototype/MVP | Both | FYP-I Weeks 14–16 |
| Sprint 3 – Core Implementation | Implement main modules | Backend, frontend, database integration, authentication, appointment management, routing, escalation workflows | Working Core System, Integrated Modules | Both | FYP-II Weeks 1–8 |
| Sprint 4 – Testing & Refinement | Validate and improve system | Testing, bug fixing, usability improvements, validation activities | Test Report, Test Evidence, Refined System | Both | FYP-II Weeks 9–12 |
| Finalization Sprint | Prepare final submission | Final report writing, presentation preparation, repository cleanup, demo preparation | Final Report, Final Presentation, Final Repository | Both | FYP-II Weeks 13–16 |

# 9. Design Update Plan

Since Agile/Iterative projects evolve during development, design artifacts shall be reviewed and updated whenever major changes occur.

| Design Artifact | Initial Version Planned | Update Trigger | Final Version Expected |
| --- | --- | --- | --- |
| High-Level Architecture & Risk Analysis | CP1 | Major architecture or technology stack change | CP4 |
| Software Design Document | CP2 | Major module, API, database, or UI modification | CP4 |
| ERD / Database Schema | CP2 | Entity, table, or relationship modification | CP4 |
| UML / System Models | CP2 | Workflow or module changes | CP4 |
| API / Interface Design | CP2 | Endpoint or interface changes | CP4 |

# 10. Milestones and Checkpoints

| Milestone | Expected Timeline | Required Deliverables | Status |
| --- | --- | --- | --- |
| Topic Proposal Defence | FYP-I Week 7 | Topic Approval Form, Proposal Defence Presentation | Completed |
| Checkpoint 1 | FYP-I Week 13 | SRS, Existing Solutions Analysis, Architecture & Risk Analysis, Project Plan, GitHub Repository | Pending |
| Checkpoint 2 | FYP-I Week 16 | Software Design Document, ERD/UML, Prototype/MVP, README, Code Review Checklist | Pending |
| Checkpoint 3 | FYP-II Week 8 | Working Core System, Integrated Modules, Test Report, Test Evidence, Repository Review | Pending |
| Checkpoint 4 | FYP-II Week 15 | Complete System, Final Report Draft, Final Testing Evidence, Final Presentation Draft | Pending |
| Final Defence | FYP-II Week 16 | Final Report, Final Presentation, Live Demonstration, Final Repository | Pending |

# 11. Sprint Review / Progress Monitoring

| Review No. | Tentative Week | Review Type | Agenda |  | Expected Outcome |
| --- | --- | --- | --- | --- | --- |
| 1 | FYP-I Week 8 | Supervisor Review | Review proposal feedback and finalize scope | Revised project scope |
| 2 | FYP-I Week 10 | Supervisor Review | Review SRS and requirements | Requirements baseline |
| 3 | FYP-I Week 12 | Supervisor Review | Review architecture, risks, and technology stack | Architecture baseline |
| 4 | FYP-I Week 15 | Sprint Review | Review software design and MVP preparation | Checkpoint-2 readiness |
| 5 | FYP-II Week 5 | Sprint Review | Review implementation progress | Core module completion |
| 6 | FYP-II Week 10 | Sprint Review | Review testing and integration | Testing improvement plan |
| 7 | FYP-II Week 14 | Final Review | Final report and demonstration review | Final readiness |

The group shall maintain regular coordination with the assigned supervisor throughout FYP-I and FYP-II.

# 12. Resources Required

| Resource Category | Details |
| --- | --- |
| Hardware | Laptop/Desktop Computers, Internet Connectivity |
| Software / Tools | Visual Studio Code, GitHub, Draw.io, MS Word |
| Programming Languages | HTML, CSS, JavaScript |
| Frameworks / Libraries | Node.js, Express.js |
| Database | MySQL |
| APIs / External Services | Web Speech API, Optional WhatsApp Integration |
| Dataset / Test Data | Simulated hospital, patient, doctor, and appointment data |
| Deployment Platform | Local Server, Render, or Cloud-Based Hosting |

# 13. Risk Register

| Risk | Type | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- |
| WhatsApp API unavailable | Technical | High | Medium | Use web-based chatbot as primary channel | Both |
| Intent misclassification | Technical | Medium | High | Human escalation workflow | Ibtisam |
| Appointment scheduling conflicts | Functional | Medium | Medium | Availability validation and conflict checking | Ibtisam |
| Scope expansion during development | Scope | Medium | High | Follow approved requirements and supervisor guidance | Both |
| Limited real hospital data | Resource | High | Medium | Use realistic simulated data and document assumptions | Both |
| Browser compatibility issues | Technical | Low | Medium | Cross-browser testing | Faryal |
| Uneven team contribution | Team | Low | High | Clear ownership and GitHub activity tracking | Both |
| Security vulnerabilities | Security | Medium | High | RBAC, password hashing, input validation | Ibtisam |
| Voice API limitations | Technical | Medium | Low | Treat voice support as enhancement feature | Both |
| Development delays | Resource | Medium | High | Milestone tracking and regular reviews | Both |

# 14. Deliverables Summary

| Deliverable | Planned Stage | Responsible Student(s) | Status |
| --- | --- | --- | --- |
| Topic Approval Form | Topic Defence | Both | Completed |
| Proposal Defence Presentation | Topic Defence | Both | Completed |
| SRS | CP1 | Both | Pending |
| Existing Solutions Analysis | CP1 | Both | Pending |
| High-Level Architecture & Risk Analysis | CP1 | Both | Pending |
| Project Plan | CP1 | Both | Pending |
| Software Design Document | CP2 | Both | Pending |
| Prototype / MVP | CP2 | Both | Pending |
| Testing Plan / Test Report | CP3 | Both | Pending |
| Final Report | CP4 / Final Defence | Both | Pending |

# 15. GitHub Repository Plan

| Item | Details |
| --- | --- |
| Repository Name | FYP-2026-G2-HybridIntelligentSystemforPatientQueryHandlingAndAppointmentManagement |
| Repository Link | https://github.com/ibtisamkhan369-ik/FYP-2026-G2-HybridIntelligentSystemforPatientQueryHandlingAndAppointmentManagement |
| Access Shared With | Group Members, Supervisor, FYP Coordinator, Department Head |
| Initial Documents Uploaded | Topic Approval Form, Proposal Defence Presentation |
| Minimum Repository Folders | /docs, /src, /test, /presentations, /reports, /evidence |
| Recommended Repository Structure | /01-Topic-Approval, /02-Project-Plan, /03-Requirements-SRS, /04-Architecture-Risk, /05-Software-Design, /06-Prototype, /07-Development, /08-Testing, /09-Security, /10-Reviews, /11-Presentations, /12-Final-Report, /13-Final-Deliverables |

# 16. Gantt Chart / Roadmap

| Phase | Timeline | Responsible Students | Deliverables |
| --- | --- | --- | --- |
| Requirements Engineering | FYP-I Weeks 9–10 | Both | SRS, Literature Analysis |
| Architecture & Risk Analysis | FYP-I Weeks 11–12 | Both | Architecture & Risk Analysis |
| Checkpoint-1 | FYP-I Week 13 | Both | CP1 Submission |
| Software Design & MVP | FYP-I Weeks 14–16 | Both | SDD, ERD, UML, MVP |
| Core Development | FYP-II Weeks 1–8 | Both | Working System |
| Testing & Validation | FYP-II Weeks 9–12 | Both | Test Reports, Validation Evidence |
| Final Documentation | FYP-II Weeks 13–14 | Both | Final Report |
| Checkpoint-4 | FYP-II Week 15 | Both | Final Readiness Review |
| Final Defence | FYP-II Week 16 | Both | Final Deliverables |

# 17. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Student 1 | Ibtisam Saleem | __________ | __________ |
| Student 2 | Faryal Israr | __________ | __________ |
| Supervisor | Ma’am Madiha Zaidi | __________ | __________ |